## Task List
Task ID | Task Name | Category | Start Date | End Date | Duration (Days) | Notes
1 | Project initialization and base setup | Planning and Setup | 2025-11-02 | 2025-11-02 | 1 | Initial project setup and repository foundation.
2 | Dashboard and event list UI improvements | Frontend Development | 2025-11-10 | 2025-11-10 | 1 | Updated dashboard and event list components with improved styles and functionality.
3 | Face recognition integration and event indexing | Backend Development | 2025-11-10 | 2025-11-10 | 1 | Added face recognition support and event date indexing for performance.
4 | Audit log improvements and fixes | Security and Monitoring | 2025-11-10 | 2025-11-11 | 2 | Updated audit trail behavior and fixed related paths and minor issues.
5 | Admin flow enhancement and resident creation restrictions | Backend and Access Control | 2025-11-24 | 2025-11-24 | 1 | Enhanced admin behavior and removed public resident creation.
6 | Notification and navigation improvements | Frontend Development | 2025-11-25 | 2025-11-25 | 1 | Improved toast notifications and added create-event access in navigation.
7 | Forgot password and one-time code reset flow | Authentication | 2025-11-27 | 2025-11-27 | 1 | Implemented forgot password and OTP-based reset flow.
8 | Navigation rebrand and portal UI refinements | Frontend Development | 2025-11-27 | 2025-12-01 | 5 | Rebranded top bar, improved UI, and added resident/admin verification-related interface updates.
9 | Major UI refresh and visual redesign | Frontend Development | 2026-03-21 | 2026-03-23 | 3 | Refreshed system appearance, backgrounds, camera UI, and resident portal layout.
10 | Face library fixes and scanner improvements | Face Recognition | 2026-03-22 | 2026-03-26 | 5 | Stabilized face stack, scanner behavior, camera access, and face matching.
11 | Event registrants, analytics, and event issue fixes | Events and Analytics | 2026-03-22 | 2026-03-23 | 2 | Improved analytics, adjusted layout, and fixed event-related issues.
12 | Deployment notes and cloud deployment preparation | Deployment and Documentation | 2026-03-22 | 2026-03-31 | 10 | Cleaned runtime files and prepared deployment, archival, and AWS hosting notes.
13 | Gate portal foundation and QR-based guest entry | Gate Operations | 2026-03-23 | 2026-03-23 | 1 | Introduced gate portal flow, guest QR scanning, and unified gate history behavior.
14 | Gate portal time sheets and guard face scanner | Gate Operations | 2026-03-24 | 2026-03-24 | 1 | Added guard portal time sheets, camera support, and hardening updates.
15 | Guest appointment management module | Guest Management | 2026-03-25 | 2026-03-26 | 2 | Added guest appointment workflows, guard portal support, and manual lookup improvements.
16 | Verification status and resident table improvements | Resident Management | 2026-03-26 | 2026-03-26 | 1 | Improved verified status visibility and resident table behavior.
17 | Email-based reset and registration validation improvements | Authentication | 2026-03-27 | 2026-03-27 | 1 | Added temporary email reset flow and required email during registration.
18 | Resident registration face enrollment integration | Resident Management | 2026-03-30 | 2026-03-30 | 1 | Added face capture to resident registration and fixed multi-sample face enrollment regression.
19 | Sidebar, logo, and dashboard UI refinements | Frontend Development | 2026-03-30 | 2026-03-30 | 1 | Refined dashboard visuals, branding, and layout details.
20 | Resident data masking and privacy improvements | Security and Privacy | 2026-03-30 | 2026-03-30 | 1 | Masked resident email, phone, and address in list view by default.
21 | AWS archival | Archival | 2026-03-30 | 2026-03-31 | 2 | archival workflow for capstone
22 | Admin and resident login UI refresh | Frontend Development | 2026-04-06 | 2026-04-06 | 1 | Refreshed login and general UI components.
23 | Guest dashboard status dropdown filter | Guest Management | 2026-04-06 | 2026-04-06 | 1 | Added guest dashboard filtering for arrived, completed, and cancelled appointments.

## Gantt Chart
Task ID | Task Name | Category | Start Date | End Date | Duration | Nov 2025 | [28 empty] | Dec 2025 | [30 empty] | Jan 2026 | [30 empty] | Feb 2026 | [27 empty] | Mar 2026 | [30 empty] | Apr 2026
 | time axis 2025-11-02 to 2026-04-06
1 | Project initialization and base setup | Planning and Setup | 2025-11-02 | 2025-11-02 | 1
2 | Dashboard and event list UI improvements | Frontend Development | 2025-11-10 | 2025-11-10 | 1 | bar: 2025-11-10
3 | Face recognition integration and event indexing | Backend Development | 2025-11-10 | 2025-11-10 | 1 | bar: 2025-11-10
4 | Audit log improvements and fixes | Security and Monitoring | 2025-11-10 | 2025-11-11 | 2 | bar: 2025-11-10 to 2025-11-11
5 | Admin flow enhancement and resident creation restrictions | Backend and Access Control | 2025-11-24 | 2025-11-24 | 1 | bar: 2025-11-24
6 | Notification and navigation improvements | Frontend Development | 2025-11-25 | 2025-11-25 | 1 | bar: 2025-11-25
7 | Forgot password and one-time code reset flow | Authentication | 2025-11-27 | 2025-11-27 | 1 | bar: 2025-11-27
8 | Navigation rebrand and portal UI refinements | Frontend Development | 2025-11-27 | 2025-12-01 | 5 | bar: 2025-11-27 to 2025-12-01
9 | Major UI refresh and visual redesign | Frontend Development | 2026-03-21 | 2026-03-23 | 3 | bar: 2026-03-21 to 2026-03-23
10 | Face library fixes and scanner improvements | Face Recognition | 2026-03-22 | 2026-03-26 | 5 | bar: 2026-03-22 to 2026-03-26
11 | Event registrants, analytics, and event issue fixes | Events and Analytics | 2026-03-22 | 2026-03-23 | 2 | bar: 2026-03-22 to 2026-03-23
12 | Deployment notes and cloud deployment preparation | Deployment and Documentation | 2026-03-22 | 2026-03-31 | 10 | bar: 2026-03-22 to 2026-03-31
13 | Gate portal foundation and QR-based guest entry | Gate Operations | 2026-03-23 | 2026-03-23 | 1 | bar: 2026-03-23
14 | Gate portal time sheets and guard face scanner | Gate Operations | 2026-03-24 | 2026-03-24 | 1 | bar: 2026-03-24
15 | Guest appointment management module | Guest Management | 2026-03-25 | 2026-03-26 | 2 | bar: 2026-03-25 to 2026-03-26
16 | Verification status and resident table improvements | Resident Management | 2026-03-26 | 2026-03-26 | 1 | bar: 2026-03-26
17 | Email-based reset and registration validation improvements | Authentication | 2026-03-27 | 2026-03-27 | 1 | bar: 2026-03-27
18 | Resident registration face enrollment integration | Resident Management | 2026-03-30 | 2026-03-30 | 1 | bar: 2026-03-30
19 | Sidebar, logo, and dashboard UI refinements | Frontend Development | 2026-03-30 | 2026-03-30 | 1 | bar: 2026-03-30
20 | Resident data masking and privacy improvements | Security and Privacy | 2026-03-30 | 2026-03-30 | 1 | bar: 2026-03-30
21 | AWS archival and cloud readiness | Deployment and Archival | 2026-03-30 | 2026-03-31 | 2 | bar: 2026-03-30 to 2026-03-31
22 | Admin and resident login UI refresh | Frontend Development | 2026-04-06 | 2026-04-06 | 1 | bar: 2026-04-06
23 | Guest dashboard status dropdown filter | Guest Management | 2026-04-06 | 2026-04-06 | 1 | bar: 2026-04-06